CONDIGENCE LLP

AI Agentic Operations System

Statement of Work & Delivery Work Plan

Prepared for internal execution tracking - shareable with client

Version 1.0

# 1. Project Overview

Condigence LLP is building an AI-powered virtual management layer that mirrors its existing org structure: Owner → AI CEO → Agentic Layer → specialized department agents (Comms, Finance, Compliance, Project, HR, Analytics) → underlying business systems (Zoho Books, Zoho CRM, Notion, Gmail, WhatsApp). The system drafts, tracks, and reports across operations, finance, compliance, and HR - with the human owner retaining approval authority over financial, legal, and client-facing actions.

# 2. Governing Principle: Human-in-the-Loop

- Payments, payroll disbursement, and any money movement: agent drafts, human approves - nothing auto-executes.

- GST/MCA/ROC filings and other compliance actions: agent drafts and tracks deadlines, human files.

- Client-facing communication: draft + approval queue by default; auto-send only for a proven-safe subset after a trust period.

- Every agent action is written to an audit log (who/what/when) so any decision can be traced back.

# 3. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Agent Orchestration | LangGraph + Python | Central routing, state management, multi-agent execution (single framework - CrewAI dropped to avoid overlap) |
| LLM | OpenAI GPT | Reasoning, drafting, classification, summarization |
| Workflow Automation | n8n | Reminders, scheduled syncs, deterministic integrations |
| Finance | Zoho Books | Invoicing, GST, expenses, accounting |
| CRM | Zoho CRM | Leads, clients, deals, communication history |
| Project Management | Notion | Projects, tasks, deadlines, SOPs |
| Database | MongoDB | App data, agent runs, tasks, approvals, audit records |
| Cache / Queue | Redis | Caching, locks, rate limiting, queues |
| Knowledge Base | Pinecone | Vector search over SOPs, policies, contracts |
| Backend API | FastAPI | API layer connecting agents, DB, business systems, frontend |
| Frontend | React | Owner dashboard, reports, approvals |
| Auth | JWT + OAuth 2.0 | Authentication, roles, secure API access |
| Email | Gmail API | Reading, sending, processing business email |
| Notifications | WhatsApp Business API + Email + Slack | Alerts, reminders, approval requests |
| Deployment | AWS + Docker | Hosting, containerization, scalability |

# 4. Phase Summary

| Phase | Duration | Focus Area | Client Checkpoint |
| --- | --- | --- | --- |
| Phase 1 | Week 1 - 4 | Foundation: infra, auth, AI CEO skeleton, WhatsApp API application, dashboard shell | Skeleton demo + scope sign-off |
| Phase 2 | Week 5 - 10 | Core agents: Comms Agent + Finance Agent, Operations Manager routing, approval workflows | Live demo of Comms + Finance |
| Phase 3 | Week 11 - 16 | Compliance, Project, HR, Analytics Agents + Knowledge Base (RAG) | Live demo of all 6 agents |
| Phase 4 | Week 17 - 20 | Integration, security hardening, UAT, AWS deployment, training, go-live | Final handoff & sign-off |

Total duration: approximately 20 weeks (5 months) for a working v1 with human approval gates on all financial and legal actions. Timeline can compress if the agent count is trimmed for v1 (e.g., ship Comms + Finance + Analytics first, defer HR/Compliance to v1.1), or extend if Zoho/Notion API integration or WhatsApp Business API approval takes longer than expected.

# 5. Detailed Week-by-Week, Day-wise Work Plan

Use this section to track daily execution. Each week is colour-coded by phase (Phase 1 = blue, Phase 2 = green, Phase 3 = orange, Phase 4 = purple).

Week 1  |  Phase 1  -  Kickoff & Infra Setup

| Day 1 (Mon) | Client requirement call - confirm scope, list which agent actions are draft-only vs. auto-executed |
| --- | --- |
| Day 2 (Tue) | Finalize tech stack decisions; set up GitHub repo and project structure |
| Day 3 (Wed) | FastAPI backend skeleton + MongoDB connection + environment configs |
| Day 4 (Thu) | Redis setup + JWT/OAuth authentication skeleton |
| Day 5 (Fri) | Submit WhatsApp Business API application (long approval lead time - start early) |

Week 2  |  Phase 1  -  Data Model & Orchestration Skeleton

| Day 1 (Mon) | Design DB schema: users, agents, tasks, approvals, audit logs |
| --- | --- |
| Day 2 (Tue) | Build RBAC roles mapped to org chart (Owner, AI CEO, Ops Manager, Accounts Assistant) |
| Day 3 (Wed) | Set up LangGraph orchestration framework + basic agent scaffolding |
| Day 4 (Thu) | Build AI CEO routing skeleton (message routing between placeholder agents, no real logic yet) |
| Day 5 (Fri) | React dashboard shell - project setup, auth pages, layout |

Week 3  |  Phase 1  -  Business System Connections

| Day 1 (Mon) | Dashboard: empty-state pages for each agent + navigation |
| --- | --- |
| Day 2 (Tue) | Zoho Books API research + sandbox account setup |
| Day 3 (Wed) | Zoho CRM API research + sandbox setup |
| Day 4 (Thu) | Notion API integration setup |
| Day 5 (Fri) | Gmail API setup + OAuth consent screen |

Week 4  |  Phase 1  -  Audit Trail & Phase 1 Review

| Day 1 (Mon) | Audit-log design + implementation (every agent action logged to Mongo) |
| --- | --- |
| Day 2 (Tue) | n8n install/host + first test workflow (scheduled reminder email) |
| Day 3 (Wed) | Internal end-to-end test of Phase 1 skeleton |
| Day 4 (Thu) | Buffer / bug fixes |
| Day 5 (Fri) | Phase 1 demo with client - confirm scope for Phase 2 |

Week 5  |  Phase 2  -  Comms Agent

| Day 1 (Mon) | Comms Agent - design drafting logic/prompts for email |
| --- | --- |
| Day 2 (Tue) | Comms Agent - Gmail read/send integration (draft-only mode) |
| Day 3 (Wed) | Comms Agent - approval queue UI in dashboard |
| Day 4 (Thu) | WhatsApp integration - basic send/receive (if approved by now) |
| Day 5 (Fri) | Test Comms Agent with sample client emails |

Week 6  |  Phase 2  -  Finance Agent

| Day 1 (Mon) | Finance Agent - invoice drafting logic + Zoho Books invoice API |
| --- | --- |
| Day 2 (Tue) | Finance Agent - GST calculation logic |
| Day 3 (Wed) | Finance Agent - expense tagging & categorization |
| Day 4 (Thu) | Finance Agent - approval workflow (draft -> owner approves -> send) |
| Day 5 (Fri) | Test Finance Agent workflows end-to-end |

Week 7  |  Phase 2  -  Operations Manager & Automation

| Day 1 (Mon) | Operations Manager - client communication routing logic |
| --- | --- |
| Day 2 (Tue) | Operations Manager - vendor management workflows |
| Day 3 (Wed) | Operations Manager - approval escalation logic |
| Day 4 (Thu) | n8n workflows - deadline reminders, scheduled syncs |
| Day 5 (Fri) | n8n workflows - notification integration (Email/Slack) |

Week 8  |  Phase 2  -  Dashboard & Integration

| Day 1 (Mon) | Wire audit logging into Comms + Finance agents |
| --- | --- |
| Day 2 (Tue) | Dashboard - approval queue page (payments, documents to sign) |
| Day 3 (Wed) | Dashboard - weekly summary report generation |
| Day 4 (Thu) | Test full Ops + Finance flow end-to-end |
| Day 5 (Fri) | Bug fixes |

Week 9  |  Phase 2  -  Security & Feedback

| Day 1 (Mon) | Security review of Phase 2 (auth, permissions on financial actions) |
| --- | --- |
| Day 2 (Tue) | Performance/load testing of agent response times |
| Day 3 (Wed) | Internal dry-run with team - collect feedback |
| Day 4 (Thu) | Refinement based on feedback |
| Day 5 (Fri) | Buffer |

Week 10  |  Phase 2  -  Polish & Phase 2 Review

| Day 1-4 (Mon-Thu) | Final polish of Comms + Finance Agents; fix edge cases |
| --- | --- |
| Day 5 (Fri) | Phase 2 demo with client - confirm scope for Phase 3 |

Week 11  |  Phase 3  -  Compliance Agent

| Day 1 (Mon) | MCA/ROC deadline calendar data model |
| --- | --- |
| Day 2 (Tue) | Compliance Agent - deadline tracking logic |
| Day 3 (Wed) | Compliance Agent - filing reminder workflow (n8n) |
| Day 4 (Thu) | Compliance Agent - escalation logic when overdue |
| Day 5 (Fri) | Test Compliance Agent |

Week 12  |  Phase 3  -  Project Agent

| Day 1 (Mon) | Notion integration - task/project sync |
| --- | --- |
| Day 2 (Tue) | Project Agent - deadline tracking logic |
| Day 3 (Wed) | Project Agent - status report generation |
| Day 4 (Thu) | Project Agent - task follow-up reminders |
| Day 5 (Fri) | Test Project Agent |

Week 13  |  Phase 3  -  HR Agent

| Day 1 (Mon) | HR Agent - leave tracking logic |
| --- | --- |
| Day 2 (Tue) | HR Agent - payroll info assist (read-only) |
| Day 3 (Wed) | HR Agent - employee reminders / onboarding checklist |
| Day 4 (Thu) | HR data model + permissions (sensitive data handling) |
| Day 5 (Fri) | Test HR Agent |

Week 14  |  Phase 3  -  Analytics Agent

| Day 1 (Mon) | Analytics Agent - revenue report generation from Zoho Books |
| --- | --- |
| Day 2 (Tue) | Analytics Agent - monthly P&L report |
| Day 3 (Wed) | Analytics Agent - dashboard visualizations (charts) |
| Day 4 (Thu) | Analytics Agent - automated monthly report scheduling |
| Day 5 (Fri) | Test Analytics Agent |

Week 15  |  Phase 3  -  Knowledge Base (RAG)

| Day 1 (Mon) | Pinecone vector DB setup |
| --- | --- |
| Day 2 (Tue) | Ingest SOPs, policies, contracts into knowledge base |
| Day 3 (Wed) | Connect knowledge base to agents (RAG) for policy-aware answers |
| Day 4 (Thu) | Test knowledge retrieval accuracy |
| Day 5 (Fri) | Buffer / refinement |

Week 16  |  Phase 3  -  Full Agent Integration & Phase 3 Review

| Day 1-3 (Mon-Wed) | Integration test of all 6 agents together under the Agentic Layer |
| --- | --- |
| Day 4 (Thu) | Bug fixes |
| Day 5 (Fri) | Phase 3 demo with client - confirm scope for Phase 4 |

Week 17  |  Phase 4  -  End-to-End Testing & Security

| Day 1 (Mon) | End-to-end test: AI CEO -> all agents -> business systems |
| --- | --- |
| Day 2 (Tue) | Security audit - permissions/RBAC across all agents |
| Day 3 (Wed) | Security audit - data encryption, API key management |
| Day 4 (Thu) | Load / stress testing |
| Day 5 (Fri) | Bug fixes |

Week 18  |  Phase 4  -  Dashboard Polish & UAT Round 1

| Day 1 (Mon) | Owner dashboard - weekly summary finalization |
| --- | --- |
| Day 2 (Tue) | Owner dashboard - approvals & e-sign integration |
| Day 3 (Wed) | Notification system polish (WhatsApp/Email/Slack) |
| Day 4 (Thu) | UAT session 1 - with Operations Manager & Accounts Assistant |
| Day 5 (Fri) | Fix UAT feedback |

Week 19  |  Phase 4  -  UAT Round 2 & Deployment

| Day 1 (Mon) | UAT session 2 - with designated partners (Wife / Mother) |
| --- | --- |
| Day 2 (Tue) | Fix UAT feedback |
| Day 3 (Wed) | AWS deployment setup - Docker containers, staging environment |
| Day 4 (Thu) | AWS production deployment |
| Day 5 (Fri) | Monitoring / alerting setup |

Week 20  |  Phase 4  -  Documentation, Training & Go-Live

| Day 1 (Mon) | Technical documentation |
| --- | --- |
| Day 2 (Tue) | User guide for owner/team |
| Day 3 (Wed) | Training session with client team |
| Day 4 (Thu) | Final bug fixes, handoff prep |
| Day 5 (Fri) | Final handoff & go-live |

# 6. Assumptions & Dependencies

- Client provides timely access/credentials for Zoho Books, Zoho CRM, Notion, Gmail, and WhatsApp Business Manager.

- WhatsApp Business API verification is a third-party (Meta) approval process and may take 1-3 weeks outside our control - hence started in Week 1.

- Scope for each phase is confirmed with the client at the checkpoint demo before the next phase begins.

- OpenAI API usage, Zoho, Notion, Pinecone, and AWS hosting costs are billed separately as pass-through infrastructure costs.

- Any request outside the agreed phase scope is treated as a change request and scheduled separately.

# 7. Sign-off

This document, once reviewed, serves as the working plan between Condigence LLP and the delivery team for the AI Agentic Operations System build.

Prepared by: Rishav Patel        Date: 11-08-2026

Approved by (Owner - Vishal Aryan): _______________________        Date: _______________